## Product Backlog
Project Name | School Management And Reporting Tool (SMART)
Product Name: | SMART | [6 empty] | Complete Fields in Green!!!
Team ID: | Sigala
| Team Member Name | [5 empty] | Initials | Student ID
Required | William Sigala | [5 empty] | WTS | 1001730022
Sprint # | Remaining | Completed This Sprint |  |  |  | Comment
0 | 26 |  |  |  | Total | Total number of features (in column H)
1 | 22 | 4 |  |  | 1 | Total features left at the end of Sprint #1
2 | 16 | 6 |  |  | 2 | Total features left at the end of Sprint #2
3 | 11 | 5 |  |  | 3 | ...and so on
4 | 11 | 0
5 | 11 | 0
©2016-2021 by George F. Rice
This work is licensed under a Creative Commons Attribution 4.0 International License. | [6 empty] | Note: Priority and specs for unfinished Features is subject to change at the end of each sprint at the whim of the Product Owner
Additional features may be proposed by the student but must be approved by the Product Owner in writing
Features
Feature ID | Priority | Required | Bonus | Est | Planned | Status | As a(n)… | I want to... | So that I can… | Notes
PERSON | 1 | 1 |  | 13 | 1 | Finished in Sprint 1 | Administrator | Track people’s names and email addresses | Find and contact them | Need a Person base class with to_string / operator<< name and a full_info method
STUDENT | 2 | 1 |  | 8 | 1 | Finished in Sprint 1 | Administrator | Track students by grade | Verify students’ progress | Need a Student derived class that includes the grade level (1-12)
PARENT | 3 | 1 |  | 3 | 1 | Finished in Sprint 1 | Administrator | Track parents | Coordinate on student progress | Need a Parent derived class
RELATE | 4 | 1 |  | 5 | 1 | Finished in Sprint 1 | Administrator | Associate each student with parents bidirectionally | Know which parents to contact | Mutual aggregate relationship
WINDOW | 5 | 2 |  | 13 | 2 | Finished in Sprint 2 | All | Use a windowed rather than command line interface | Use SMART more intuitively | Create a main window with a menu bar, data area, and status bar
D_STUDENT | 6 | 2 |  | 8 | 2 | Finished in Sprint 2 | Administrator | Create students via dialogs | Conveniently enter the data | Series of dialogs, one per constructor parameter, is OK
DISPLAY | 7 | 2 |  | 5 | 2 | Finished in Sprint 2 | Teacher | See all current data in the main window | Keep up with students | Display full_info for students and parents in a table in the data area
D_PARENT | 8 | 2 |  | 5 | 2 | Finished in Sprint 2 | Administrator | Create parents via dialogs | Conveniently enter the data | Series of dialogs, one per constructor parameter, is OK
D_RELATE | 9 | 2 |  | 8 | 2 | Finished in Sprint 2 | Administrator | Relate students to parents via dialogs | Conveniently enter the data | Dialog listing students and entering index, then same for parents
NEW | 10 | 2 |  | 2 | 2 | Finished in Sprint 2 | Administrator | Clear all data | Start a new school | Simply clear all elements from the vectors
SAVE | 11 | 3 |  | 13 | 3 | Finished in Sprint 3 | All | Write the data to persistent storage | Don’t have to re-enter data | See Lecture 15 for an object-oriented strategy to create the file format
LOAD | 12 | 3 |  | 8 | 3 | Finished in Sprint 3 | All | Load data for a school from persistent storage | Don’t have to re-enter data | Select file via a file chooser dialog
SAVEAS | 13 | 3 |  | 8 | 3 | Finished in Sprint 3 | Administrator | Save data to a different filename | Create backups or baselines for new schools | Select filename via a file chooser dialog
TOOLBAR | 14 | 3 |  | 5 | 3 | Finished in Sprint 3 | All | Use the major features via a toolbar | Point and click | Suggest using the Nim game’s toolbar as a baseline
ABOUT | 15 | 3 |  | 1 | 3 | Finished in Sprint 3 | Administrator | Display an About dialog with creator and version | Quickly determine which version is installed | Use Gtk::AboutDialog
COURSE | 16 | 4 |  | 21
SEMESTER | 17 | 4 |  | 8
SECTION | 18 | 4 |  | 5
19
20
21
SUBJECT | 22 | 5
TEACHER | 23 | 5 |  | 21
GRADE | 24 | 5 |  | 5
TRANSCRIPT | 25 | 5 |  | 8
ITERATORS | 26 | 5 |  | 8
BONUS WORK – COMPLETE ABOVE FEATURES FIRST!!!

## Sprint 01 Backlog
Sprint # | 1 |  | Complete Fields in Green!!!
Start on | 2021-03-02 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2021-03-09
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 10
Day 1 Left | 7 | 3
Day 2 Left | 7 | 0
Day 3 Left | 0 | 7
Day 4 Left | 0 | 0
Day 5 Left | 0 | 0
Day 6 Left | 0 | 0
Day 7 Left | 0 | 0
Note: Due to the late project start, the results of this sprint will be provided to you (although you may use your own solution if you prefer)
Task ID | Feature ID | Assigned To | Task | Status | Notes
1 | PERSON |  | Code person.h | Completed Day 1
2 | PERSON |  | Code person.cpp | Completed Day 1
3 | PERSON |  | Test compile Person class | Completed Day 1
4 | STUDENT |  | Code student.h | Completed Day 3
5 | STUDENT |  | Code student.cpp | Completed Day 3
6 | STUDENT |  | Test compile Student class | Completed Day 3
7 | PARENT |  | Duplicate Student to Parent | Completed Day 3
8 | PARENT |  | Remove grade, update to_string() and full_info() | Completed Day 3
9 | PARENT |  | Test compile Parent class | Completed Day 3
10 | RELATE |  | Build with example code and verify | Completed Day 3
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 02 Backlog
Sprint # | 2 |  | Complete Fields in Green!!!
Start on | 2021-03-09 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2021-03-23
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 10
Day 1 Left | 10 | 0
Day 2 Left | 10 | 0
Day 3 Left | 10 | 0
Day 4 Left | 10 | 0
Day 5 Left | 6 | 4
Day 6 Left | 2 | 4
Day 7 Left | 0 | 2
ADD tasks below to complete each feature for THIS sprint
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 | WINDOW | WTS | Code mainwin.h | Completed Day 5
2 | WINDOW | WTS | Code mainwin.cpp | Completed Day 5
3 | WINDOW | WTS | Test comple Mainwin class | Completed Day 5
4 | DISPLAY | WTS | Code for display label | Completed Day 6
6 | D_STUDENT | WTS | Code method for displaying students | Completed Day 6
8 | D_PARENT | WTS | Code method for displaying parents | Completed Day 6
9 | DISPLAY | WTS | Test compile Mainwin class for displaying students and parents | Completed Day 6
11 | D_RELATE | WTS | Code method for relate | Completed Day 7
13 | DISPLAY | WTS | Test compile Mainwin class for displaying student and parent relationships | Completed Day 7
14 | NEW | WTS | Code for new school | Completed Day 5
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 03 Backlog
Sprint # | 3 |  | Complete Fields in Green!!!
Start on | 2021-03-23 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2021-03-30
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 5
Day 1 Left | 5 | 0
Day 2 Left | 5 | 0
Day 3 Left | 5 | 0
Day 4 Left | 5 | 0
Day 5 Left | 5 | 0
Day 6 Left | 2 | 3
Day 7 Left | 0 | 2
ADD tasks below to complete each feature for THIS sprint
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 | SAVE | WTS | Code method for save file | Completed Day 6
2 | LOAD | WTS | Code method for load file | Completed Day 6
3 | SAVEAS | WTS | Code method for saveas file | Completed Day 6
4 | TOOLBAR | WTS | Code toolbar | Completed Day 7
5 | ABOUT | WTS | Code about | Completed Day 7
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 04 Backlog
Sprint # | 4 |  | Complete Fields in Green!!!
Start on | 2021-04-06 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2021-04-13
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 0
Day 1 Left | 0 | 0
Day 2 Left | 0 | 0
Day 3 Left | 0 | 0
Day 4 Left | 0 | 0
Day 5 Left | 0 | 0
Day 6 Left | 0 | 0
Day 7 Left | 0 | 0
ADD tasks below to complete each feature for THIS sprint
Task ID | Feature ID | Assigned To | Description | Status | Notes
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 05 Backlog
Sprint # | 5 |  | Complete Fields in Green!!!
Start on | 2021-04-13 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2021-04-20
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 0
Day 1 Left | 0 | 0
Day 2 Left | 0 | 0
Day 3 Left | 0 | 0
Day 4 Left | 0 | 0
Day 5 Left | 0 | 0
Day 6 Left | 0 | 0
Day 7 Left | 0 | 0
ADD tasks below to complete each feature for THIS sprint
Task ID | Feature ID | Assigned To | Description | Status | Notes
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84